## Sprint Backlog
Sprint 03 - Sprint Backlog - LeRoy
[7 empty] | Dag | 1 | 2 | W | W | 3 | 4 | W | W | 5 | Groene cellen niet schrappen !!! | Niet gestart
Product Backlog | Component | Product Backlog Taak | Sprint Taak Beschrijving | Opmerkingen | Status | Uitvoerder | Orig Geschat Hrs | 2012-12-03 | 2012-12-07 | 2012-12-08 | 2012-12-09 | 2012-12-10 | 2012-12-14 | 2012-12-15 | 2012-12-16 | 2012-12-17 | einde | Bezig
[7 empty] | overblijvend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Klaar
Product Backlog Taken | [16 empty] | 0
| Algemeen | Bugfixing |  |  |  | - | 0 | [9 empty] | 0
| GUI | rooster opvragen voor heel de week per lokaal |  |  | Bezig | Bedir, Nico | 60 | 0 | [8 empty] | 0
| GUI | extra pagina voor de parser (groot tekstvlak voor copy paste) |  |  |  |  | 60 | 0 | [8 empty] | 0
| GUI | extra pagina voor het resultaat |  |  |  |  | 120 | 0 | [8 empty] | 0
| GIT | de twee branches mergen (master en services) |  |  |  |  | 120 | 0 | [8 empty] | 0
| Database | dao klasses maken (entity framework maken) |  |  | Bezig | Sander, Evert | 240 | 0 | [8 empty] | 0
| Parser | integreren in het project als branches gemerged zijn |  |  | Bezig | Bart Amir | 240 | 0 | [8 empty] | 0
| Webservices | optimalisatie webservice |  |  | Bezig | Nico Selim | 240 | 0 | [8 empty] | 0
| Webservices | links van models linker naar elkaar, dit moet opgelost worden want het geeft fouten in de webservice |  |  | Bezig | Evert Nicolaas | 180 | 0 | [8 empty] | 0
[7 empty] | 21h | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0

## Planning
Sprint 03 - Planning Worksheet - LeRoy | [9 empty] | Grijze cellen niet overschrijven: die zijn berekend
Breng de initialen hier in ----> | Amir | Bart | Muhammet | Khurram | Sander | Evert | Selim | Nicolaas | Nico
A: Berekening van de beschikbare uren voor deze Sprint
wie: | Amir | Bart | Muhammet | Khurram | Sander | Evert | Selim | Nicolaas | Nico | Opmerkingen
Werkdagen voor deze Sprint | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Rekening houden met feestdagen en individuele verlofdagen
Werkuren voor deze Sprint | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 4
% gereserveerd voor support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% marge | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
uren marge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beschikbare uren vóór planning: | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | berekend
B: Planning Status
wie: | Amir | Bart | Muhammet | Khurram | Sander | Evert | Selim | Nicolaas | Nico | Opmerkingen
Totaal beschikbaar (hierboven berekend) | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | berekend
Totaal ingepland (vanuit Sprint Backlog pagina) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | berekend
Overblijvende niet-ingeplande uren | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8 | 12.8
Totaal beschikbare dagen vóór planning | 28.8 | berekend
Totaal aantal dagen Sprint | 3 | vast

## Verlof
Sprint 03 - Verlof - LeRoy
Reëel overblijvende uren | 16 | 12 |  |  | 8 | 4 |  |  | 0 | 4 | werkuren per dag
| ma | vr | za | zo | ma | vr | za | zo | ma
Dag | 1 | 2 | W | W | 3 | 4 | W | W | 5
Datum | 2012-12-03 | 2012-12-07 | 2012-12-08 | 2012-12-09 | 2012-12-10 | 2012-12-14 | 2012-12-15 | 2012-12-16 | 2012-12-17 | totaal
Amir | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Bart | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Muhammet | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Khurram | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Sander | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Evert | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Selim | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Nicolaas | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
Nico | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 4
32
Bij verlof vul het aantal beschikbare uren in die dag ( vb 0 of 4 )

## Individual Burndown
Sprint 03 - Individual Burndown Chart - LeRoy
Deze kolom niet schrappen
Reëel overblijvende uren | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | 4 | werkuren per dag
Dag | 1 | 2 | W | W | 3 | 4 | W | W | 5 | Groene cellen niet schrappen !!!
Datum | 2012-12-03 | 2012-12-07 | 2012-12-08 | 2012-12-09 | 2012-12-10 | 2012-12-14 | 2012-12-15 | 2012-12-16 | 2012-12-17 | einde
Amir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bart | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muhammet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Khurram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sander | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Evert | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Selim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nicolaas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nico | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burndown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Taken | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Let op: de hoeveelheid werk per persoon is niet belangrijk. Let enkel op de helling: gaat iemand te snel of te traag ?

## Impediments (hidden)
Sprint 03 - Impediments - LeRoy
Id | Datum rapportering | Beschrijving | Commentaar | Toestand | Datum toestand | Verloren mensdagen | Oplossing
1 | 2005-09-09 |  |  |  |  | 0
2 | 2005-09-12 |  |  |  |  | 2
3

## (Titles)
Basisparameters
LeRoy | <-- Naam van het project
Sprint 03 | <-- Identificatie van de Sprint.
2012-12-03 | <-- Eerste dag van de Sprint.
Sprint 03 - Planning Worksheet - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
Sprint 03 - Sprint Backlog - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
Sprint 03 - Team Burndown Chart - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
Sprint 03 - Individual Burndown Chart - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
Sprint 03 - Verlof - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
Sprint 03 - Impediments - LeRoy | <-- niet veranderen, deze cel wordt aangepast via cell A4
4 | <-- Aantal uren in een werkdag (gebruikt bij berekeningen).
<-- Sprint doel

## (Scrum Team) (hidden)
Sprint backlog
Handleiding voor het Scrum Team
Dagelijkse update
Dagelijks wordt de schatting van het aantal nog te presteren uren per taak aangepast. Dat gebeurt in het Sprint Backlog blad. De sprint taken zijn de rijen met een beschrijving in kolom D (Sprint Taak Beschrijving). Enkel die rijen mogen aangepast worden.
Per taak waaraan je vandaag gewerkt hebt, duid je aan hoeveel werk er nog aan dient gepresteerd te worden vanaf morgen. Dus je werkt steeds in de kolom van MORGEN. In principe is dit de eerste lege kolom.
Stappen
* Ga naar het Sprint Backlog blad
* Gebruik de Filter pijltjes in kolom G (Uitvoerder) om te filteren op naam, zoadat alleen jouw taken zichtbaar zijn.
* Pas alle relevante kolommen aan (taken waaraan je vandaag gewerkt hebt).
* In kolom E (Opmerkingen) plaats je eventuele opmerkingen.
* Zet de Filter terug op "All".
* Bewaar het bestand.
Verifiëren of je 'on track' bent
De beste manier om na te kijken of je het doel van de sprint gaat bereiken, is je individuele burndown bekijken
De cijfers van de individuele burndowns worden geconsolideerd in het Team Burndown blad.
De burndown bladen bevatten alleen maar cellen met berekende waarden. Beschouw ze dus maar als read-only.
Toevoegen van taken
Tijdens de Sprint kan het zijn dat er nieuwe taken ontdekt worden.
Schrappen van taken
Zet de status op "verwijderd".
Zet de initiële schatting op "0".
Een taak opnemen
Je neemt een taak op door jezelf als "uitvoerder" te plaatsen.
Verifiëer nadien in het planningblad of deze taak wel past in je schema. Dit doe je door in het planning-blad de overblijvende niet-ingeplande uren te bekijken. Deze waarde moet >0 blijven.
In principe mag je alleen taken opnemen die waren toegekend aan "Anoniem".
Een taak overnemen van een ander teamlid
Als dat ander teamlid nog geen prestaties had vervuld, dan overschrijf je gewoon de "uitvoerder".
Als dat niet het geval is, moet je eerst die lijn copiëren, en jezelf als "uitvoerder" zetten.

## (Scrum Master) (hidden)
Sprint backlog
Handleiding voor de Scrum Master
General | This tool depend on formulas typed into various cells, which makes it fragile. Until a better tool comes along, BE CAREFUL. - Keep a backup of this template, so you can confirm how cells were designed, if corrupted! - Tables - NEVER delete a top row or a leftmost/rightmost column. Or if you do, check right away that you've not corrupted anything in Planning, Burndowns, which use these as data sources
Grey cells | these indicate formulas - play with these cells carefully, and keep a backup!
Notes on each worksheet:
Titles worksheet | Why does this page exist? To avoid need for updates on multiple pages at start of each sprint, and potential miscommunication if these multiple updates are forgotten
Update the Red items so titles/dates throughout this workbook will be updated.
You can customise the titles on this page by using the formulas in column A
Planning worksheet | Why does this page exist? Short answer: multiple people working on a single task makes it hard to know who's overcommitted. Long answer: - we need to plan for the unplannable (production support, for example) using factors on the Planning worksheet. - Until our team is fully cross-trained, multiple people are required to do separate parts of features that, on an XP team, would be done by one pair. (ex: only 2 people write SQL on this team). Over time this is changing.
Remember: The contents of this page become obsolete after the Sprint starts. Planning after day 1 should be done using the Backlog and Burndown, as intended by the Scrum methodology
Section A: Fill in the first section at the start of planning
"Available Hours Before Planning:" - ensure that the formula in these cells makes sense where you work.
As you plan using the Sprint Backlog sheet, put in "original estimate hours". These are accumulated on the B Section of this Planning page.
Section B: Periodically check the B Section of this Planning worksheet to see if anyone is overcommitted. This allows you to redistribute work accurately while planning.
"Total Planned So Far:" you need to customise this to pick up information for the person represented by this line. Use the initials you use to indicate this person on the Backlog, and sub them into the SUMIF formula in the cells to the right. example: in =SUMIF('Sprint Backlog'!$H$6:$H$271,"=w" replace "=w" with your initials to make this pick up your tasks from the Backlog. You can change the first cell and copy it downward.
Sprint Backlog Worksheet | This is the classic Scrum Sprint Backlog, with the addition of an Estimated Hours column to make the Planning Worksheet page work.
To make the Planning worksheet work, you need to - make blue cells reflect actual dates of the Sprint - enter the initials of the Responsible person and - enter Original Estimate on this page. This will autopopulate into the cell for day 1 of the sprint
Deleting Sprint-day columns: is tricky, because they map to the graphs. Best to back up often, and check other pages after changes. Good luck.
Adding columns: (to help with planning or to co-ordinate with some outside tracking system) The "X" column indicates a good place to insert your extra columns without disturbing the Planning and Burndown pages. You can always hide them once the team starts using the Backlog in the Sprint.
Daily update: is intended to indicate TOMORROW's remaining work. Ex: at end of day today (or start of day tomorrow) update tomorrow's cell with work remaining at start of day. - use the Filter arrow to select your own initials in Responsible. - Now update any items whose work remaining changes.
Removing work: remember NOT to delete rows that already have hours - or if you do, your Burndown will not reflect the history of your Sprint (won't show the correction you've made in the trend line). It will be as if the item was never in the sprint. Better to just set remaining time to zero on the day you make the decision to maintain a record of what you did, and change status to "Removed" so you can see it's to be ignored thereafter.
Burndown cells contain a tricky formula. It is there so you don't have to copy data over everyday for items that don't change - remove it if you don't care. Otherwise: - during daily update, only update those cells that change. - others will populate automatically tomorrow, if not already done.
"Status Notes" - for things you don't want to forget, like "waiting for reply from Mr. Client on this" or "Do this one at same time as previous"
Rollups are used to make reading the backlog easier to review. - Scrummaster can use this item to maintain a status of the entire item. - Then she can see general status of a Product backlog item but ignore its many tasks. - use the small +/- buttons at top right of sheet to roll/unroll items.
Verify task: "verify" is what we call the last step in our process, which includes confirming that all deliverables are in final state, and transcribing information back into the Product Backlog tracking system.
"Done" column. Necessary to accurate extrapolate the Burndown angle. Don't enter values > 0 here.
Team Burndown chart tab | Classic Scrum Burndown Chart, with addition of #Tasks
Note: ALL data on this page comes from Individual Burndown page !!
"Done" Necessary to make the Burndown angle accurate. Comes from the Done column of the Sprint Backlog.
Individual Burndown Worksheet | This page serves two purposes: - table at the top is source data for the Team Burndown. DO NOT DELETE IT - graph at bottom is an innovation allowing finer followup of individual teammembers workload. Delete the graph if you don't want it. However, there are some reasons you might want to use it...
Nothing classic about the graph at the bottom of this page. Some reasons you might want to use it... This page can help you spot interesting trends per individual team member: - flatlining can indicate a never-ending task, or someone not updating backlog - a spike can signal a problem and tell you who has the problem - overcomes the "averaging" effect of the team burndown - team could be on target, but two individuals could cancel each other out if one is done all their work and the other is overcommitted. On a team with perfect habits and communication, this page would not be needed. Nuf said :-)